## Sheet1
Item | Sprint | Task Description | Developer | Estimated Hours | Schedule Start | Schedule End
W3-1 | Week 3 | Requirement Analysis and Final Requirement Gathering | Nishita | 6 | 2025-07-14 | 2025-07-17
W3-2 | Week 3 | System Testing (functional, frontend, backend) | Nishita | 8 | 2025-07-18 | 2025-07-22
W3-3 | Week 3 | Wireframe finalization for all modules | Perisha | 5 | 2025-07-23 | 2025-07-25
W3-4 | Week 3 | Final Frontend improvements and responsiveness testing | Perisha | 6 | 2025-07-26 | 2025-07-29
W3-5 | Week 3 | Final Backend bug fixes and API adjustments | Nishita | 6 | 2025-07-30 | 2025-08-02